## Sheet1
BESS PROJECT
S.No. | Major Activities | Detailed Activities |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar
|  |  |  | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
1 | Technology | a | Study of components / Raw materials used in manufacturing of BESS | bar: Nov WK1 to Nov WK2
|  | b | Study of Manufacturing Process / Process Flow | bar: Nov WK2 to Nov WK3
|  | c | Comparison of other similar technology available | bar: Nov WK3 to Nov WK4
|  | d | Understanding on BESS Capacity availability and | bar: Dec WK1 to Dec WK2
|  | e | Technology selection summary – LFP vs NMC vs Sodium-ion, key learnings | bar: Dec WK2
2 | Major Players / Competition | a | Mapping of global & Indian BESS players (cell makers, integrators, EPC) | bar: Dec WK1 to Dec WK2
|  | b | Study of players' product portfolio, capacity & technology | bar: Dec WK2 to Dec WK3
|  | c | Comparison of pricing, cost structure & business models | bar: Dec WK3 to Dec WK4
|  | d | Study of localisation plans, PLI / VGF status & upcoming capacities | bar: Jan WK1
|  | e | Market share analysis & SWOT of top competitors | bar: Jan WK1 to Jan WK2
3 | Supply Chain | a | Mapping of supply chain – cell, BMS, PCS, EMS, thermal, container | bar: Jan WK1 to Jan WK2
|  | b | Identification of domestic vs imported components & key suppliers | bar: Jan WK2 to Jan WK3
|  | c | Study of import dependency, lead times & logistics | bar: Jan WK3 to Jan WK4
|  | d | Should-cost / landed cost analysis of major components | bar: Feb WK1
|  | e | Localisation opportunities & vendor development roadmap | bar: Feb WK1 to Feb WK2
4 | Service Network | a | Study of O&M / AMC models offered by BESS players | bar: Feb WK1 to Feb WK2
|  | b | Mapping of existing service centres & field service coverage in India | bar: Feb WK2 to Feb WK3
|  | c | Study of spares requirement, warranty & performance guarantees | bar: Feb WK3
|  | d | Study of remote monitoring / EMS & predictive maintenance | bar: Feb WK4
|  | e | Proposal for service network model & coverage plan | bar: Mar WK1
5 | Recycling Network | a | Study of Battery Waste Management Rules 2022 & EPR obligations | bar: Feb WK3 to Feb WK4
|  | b | Mapping of battery recyclers & their capacities in India | bar: Mar WK1
|  | c | Study of recycling processes (hydromet, pyromet, direct) & material recovery | bar: Mar WK1 to Mar WK2
|  | d | Study of second-life applications & reverse logistics | bar: Mar WK2 to Mar WK3
|  | e | Recycling network roadmap & final project report | bar: Mar WK3 to Mar WK4